NoeDB

v2.0 -- Sprint Plan

A Distributed Embedded SQL Engine in Rust

Noe Engineering  |  Douala, Cameroun

Debut : 1 juin 2026  |  Fin : 29 mai 2027

7 phases  |  52 semaines  |  23 modules nouveaux  |  Rust

# Ce que NoeDB v2.0 ajoute sur v1.0

NoeDB v1.0 a pose les fondations : Lexer, Parser, Storage Engine (LSM), Query Planner, Consensus Raft, Engine E2E, Protocol et CLI. NoeDB v2.0 transforme ce moteur en infrastructure production-grade, enterprise-ready, et world-class.

Ce sprint de 52 semaines ajoute 23 modules critiques repartis en 7 phases. Chaque phase livre des capacites mesurables, testees, et benchmarkees.

| TLS/mTLS + gRPC | Wire protocol 100% chiffre, mutual auth, migration gRPC tonic | Ph.1 |
| --- | --- | --- |
| Prepared statements + RLS | SQL injection impossible structurellement, isolation multi-tenant | Ph.1 |
| MVCC complet | Multi-version concurrency: BEGIN/COMMIT/ROLLBACK + Snapshot Isolation | Ph.2 |
| Serializable SSI | Serializable Snapshot Isolation (Cahill 2008), 0 anomalie | Ph.2 |
| Deadlock detection | Wait-for graph, victim selection, timeout - 0 hang possible | Ph.2 |
| io_uring + zero-copy | P99 I/O reduit 30%+, sendfile vers client, MADV_HUGEPAGE | Ph.3 |
| SIMD vectorized exec | AVX2 filter 8 int64 en parallele - speedup 4-8x sur predicates | Ph.3 |
| Rayon parallel queries | Scans multi-core lineaires, hash join parallele | Ph.3 |
| LZ4 + XOR filter | SSTable -60% taille, FPR 0.4% (meilleur que Bloom) | Ph.3 |
| Group commit + query cache | Throughput writes +300%, cache LRU 80%+ hit rate OLAP | Ph.3 |
| Joint consensus | Dynamic membership: AddVoter/RemoveVoter sans downtime | Ph.4 |
| Follower reads linearisables | Throughput reads x3, tous noeuds servent les lectures | Ph.4 |
| Distributed 2PC | Transactions atomiques cross-shard, 0 incoherence | Ph.4 |
| Multi-raft sharding | Range sharding, auto-split > 1GB, auto-rebalancing | Ph.4 |
| S3 backup + restore | Disaster recovery teste, backup incremental, RTO<500ms RPO=0 | Ph.4 |
| Window functions | ROW_NUMBER, RANK, LAG, LEAD, SUM OVER - analytics complets | Ph.5 |
| JSON/JSONB + Full-text search | JSON first-class, index sur sous-champs, MATCH AGAINST < 5ms | Ph.5 |
| WASM UDFs | Fonctions custom sandboxees WASM, extensible sans recompiler | Ph.5 |
| COPY bulk + CTE recursive | 500k rows/s ingestion, WITH RECURSIVE pour graphes | Ph.5 |
| Prometheus + OpenTelemetry | Observabilite complete: metrics, traces, Grafana dashboard | Ph.6 |
| madsim + fuzz + sanitizers | 1000 seeds chaos tests, 48h fuzz, 0 memory error, 0 data race | Ph.6 |
| Python / Go / Node.js drivers | 3 drivers publies, connection pool 1000+ connexions | Ph.7 |
| mdBook documentation | Architecture, storage, Raft, query engine - docs completes | Ph.7 |

# Sprint Planning -- 52 semaines jour par jour

Debut : 1er juin 2026  |  Fin : 29 mai 2027  |  7 phases  |  52 semaines

| S# | Phase | Dates | Lundi | Mardi | Mercredi | Jeudi | Vendredi | Livrable semaine |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 -- Security & Protocol ¦ Semaines 1-6 |  |  |  |  |  |  |  |  |
| 01 | Security & Protocol | 01/06->05/06 | Integrer rustls crate - TLS 1.3 server config | Certificats auto-signes dev avec rcgen crate | TLS sur TCP listener noedb-cli et serveur | Client TLS - verification certificat serveur | Tests: handshake TLS reussi, faux cert rejete | TLS 1.3 actif, toutes connexions chiffrees |
| 02 | Security & Protocol | 08/06->12/06 | mTLS: client presente son certificat (mutual auth) | SPIFFE-style identity dans CN du certificat | Certificate pinning pour connexions cluster Raft | Hot reload: rotation certificats sans downtime | Tests: cert expire rejete, rotation sans coupure | mTLS cluster Raft, rotation certificats live |
| 03 | Security & Protocol | 15/06->19/06 | Definir proto3 schema: QueryRequest, QueryResponse, RaftRPC | Generer code Rust avec tonic-build (gRPC) | Migrer SQL protocol sur gRPC unary calls | Migrer AppendEntries et RequestVote sur gRPC | Tests: integration gRPC, backward compat protocol | gRPC remplace TCP custom: Raft + SQL unifies |
| 04 | Security & Protocol | 22/06->26/06 | Parser PREPARE stmt AS SELECT - syntax | Statement cache: HashMap<Name, CompiledPlan> | EXECUTE stmt (val1, val2) - bind typed parameters | Securite: parametres jamais interpoles - SQL injection impossible | Benchmark: prepared x1000 vs unprepared - speedup mesure | Prepared statements, SQL injection structurellement impossible |
| 05 | Security & Protocol | 29/06->03/07 | Policy struct: table + expression + role + action | ALTER TABLE t ENABLE ROW LEVEL SECURITY - parser | CREATE POLICY p ON t USING (expr) - parser + planner | Planner: injecter policy expr dans WHERE automatiquement | Tests: user A ne voit JAMAIS les rows de user B | RLS multi-tenant: isolation par policy, zero fuite |
| 06 | Security & Protocol | 06/07->10/07 | AuditEntry: tenant, user, query, ts, rows_affected | Audit log SSTable dedie, append-only, immuable | cargo-audit: scanner toutes dependances CVEs | cargo-fuzz: fuzzer parser SQL, 24h continus | SECURITY.md + CVE policy + post LinkedIn securite | Audit log actif, 0 CVE, parser fuzz-teste 24h |
| Phase 2 -- MVCC & Transactions ¦ Semaines 7-14 |  |  |  |  |  |  |  |  |
| 07 | MVCC & Transactions | 13/07->17/07 | Version struct: (key, version_ts, value, deleted_flag) | Timestamp Oracle: monotonique, distributed-safe | Modifier MemTable: multi-versions par cle (BTreeMap upgrade) | Modifier SSTable writer/reader: format multi-version | Tests: ecrire v1 puis v2 -> lire les 2 versions par timestamp | Storage multi-version: LSM MVCC-ready |
| 08 | MVCC & Transactions | 20/07->24/07 | Transaction struct: txn_id, start_ts, write_set, read_set | BEGIN: creer transaction, assigner start_ts atomique | Read-your-writes: dans une txn lire ses propres writes | COMMIT: ecrire toutes versions atomiquement avec commit_ts | ROLLBACK: purger write_set, liberer locks, marquer aborted | BEGIN/COMMIT/ROLLBACK complets, isolation basique |
| 09 | MVCC & Transactions | 27/07->31/07 | ReadView: snapshot des txns actives au moment du BEGIN | Visibility rule: version visible si commit_ts < start_ts | Non-repeatable reads impossibles: meme row = meme resultat | Phantom reads: range locks sur scans pour eviter fantomes | Tests: 100 txns concurrentes -> 0 anomalie isolation mesuree | Snapshot Isolation prouvee, 100 txns concurrentes sans anomalie |
| 10 | MVCC & Transactions | 03/08->07/08 | Lire paper SSI (Cahill 2008): Serializable Snapshot Isolation | Anti-dependency tracking: detecter write-read conflicts | Cycle detection dans dependency graph (DFS) | Abort de la txn victime en cas de cycle detecte | Tests: bank transfers - 0 incoherence sur 10k txns paralleles | SSI implemente: isolation serialisable prouvee |
| 11 | MVCC & Transactions | 10/08->14/08 | Wait-for graph: construire graphe dependances de lock | Cycle detection DFS: toutes les 100ms en background | Victim selection: aborter la transaction la plus jeune | Timeout fallback: txn attendant > 5s -> abort automatique | Tests: 50 txns provoquant deadlocks -> toutes resolues, 0 hang | Deadlock detection + resolution automatique, 0 hang possible |
| 12 | MVCC & Transactions | 17/08->21/08 | DDL transactionnel: CREATE TABLE inside BEGIN/COMMIT | Schema versioning: chaque schema porte un version_ts | Schema rollback: ROLLBACK annule le CREATE TABLE | Online schema change: ALTER TABLE COLUMN sans table lock | Tests: 10 DDL concurrentes + 100 DML -> coherence parfaite | DDL transactionnel, ALTER TABLE online sans downtime |
| 13 | MVCC & Transactions | 24/08->28/08 | Version pruner: identifier versions non visibles par aucune txn | Background GC: sweep SSTable, purger vieilles versions | Compaction MVCC-aware: jamais compacter version encore visible | Metrics: avg_versions_per_key, gc_lag_seconds - Prometheus | Tests: 1M writes -> GC -> taille stable, lectures correctes | GC automatique MVCC, espace disque stabilise |
| 14 | MVCC & Transactions | 31/08->04/09 | OLTP benchmark TPC-B style: bank transfers criterion | Mesurer: transactions/sec en mode serializable isolation | Comparer: overhead SSI vs snapshot - delta documente | Flamegraph transaction manager -> optimiser hot path | Post LinkedIn: MVCC + Transactions + tag v1.1.0-mvcc | Benchmark OLTP publie, tag v1.1.0-mvcc |
| Phase 3 -- Performance Extreme ¦ Semaines 15-24 |  |  |  |  |  |  |  |  |
| 15 | Performance Extreme | 07/09->11/09 | Etudier io_uring API (Axboe), integrer tokio-uring crate | Remplacer tokio::fs::File par io_uring pour WAL writes | io_uring pour SSTable reads avec registered buffers | Batch I/O: grouper N writes en un seul io_uring submit | Benchmark: fsync io_uring vs tokio - P99 latence reduite | io_uring WAL + SSTable: P99 reduit 30%+ |
| 16 | Performance Extreme | 14/09->18/09 | mmap SSTable files: MAP_PRIVATE + MADV_RANDOM hints | Zero-copy: retourner &[u8] slices depuis mmap sans copie | sendfile pour transferts TCP vers client (0 kernel->user copy) | Huge pages: MADV_HUGEPAGE sur mmap regions actives | Benchmark: mmap vs read() - throughput SELECT large +40% | Zero-copy reads: throughput +40% sur SELECT large tables |
| 17 | Performance Extreme | 21/09->25/09 | std::simd nightly ou packed_simd2: setup SIMD en Rust | Vectorized filter: comparer 8 valeurs int64 en parallele AVX2 | Vectorized hash: CityHash SIMD pour GROUP BY buckets | Vectorized scan: SSTable block scan avec SIMD predicates | Benchmark: SIMD filter vs scalar 1M rows - speedup 4-8x | SIMD filter AVX2: speedup 4-8x sur integer predicates |
| 18 | Performance Extreme | 28/09->02/10 | Rayon crate: parallel iterators sur les scans SSTable | Parallel SeqScan: diviser SSTable en chunks -> rayon::par_iter | Parallel hash join: build phase parallele avec rayon HashMap | Parallel aggregate: sum/count par chunks -> merge results | Tests: resultats mono == multi-thread + benchmark speedup lineaire | Parallel scan multi-core: speedup lineaire jusqu'a 8 cores |
| 19 | Performance Extreme | 05/10->09/10 | lz4-flex crate: compresser SSTable blocks a l'ecriture | Decompression transparente: hot path optimise, lazy decode | Dictionary encoding: remplacer strings repetes par IDs u16 | RLE (Run-Length Encoding): colonnes a faible cardinalite | Benchmark: taille SSTable avant/apres - cible -60% + debit maintenu | LZ4 + dict encoding + RLE: taille -60%, debit inchange |
| 20 | Performance Extreme | 12/10->16/10 | Lire paper XOR filter (Graf & Lemire 2020) | Implementer XorFilter<u8> from scratch en Rust | XorFilter<u16> pour tables larges (meilleur FPR) | Remplacer BloomFilter par XorFilter dans chaque SSTable | Tests: FPR < 0.4% (vs 1% Bloom) + taille structure -30% | XOR filter: FPR 0.4%, memoire -30% vs Bloom Filter |
| 21 | Performance Extreme | 19/10->23/10 | Cache key: hash(normalized_sql + schema_version) | LRU cache en memoire: 256MB configurable via config | Invalidation: ecriture sur table T invalide tous caches de T | Cache distribue: partager resultats via Redis cluster nodes | Benchmark: hit rate > 80% sur workload OLAP realiste | Query cache LRU actif, hit rate 80%+ sur OLAP |
| 22 | Performance Extreme | 26/10->30/10 | Batch writer: accumuler N writes avant flush WAL | Group commit: plusieurs transactions en 1 seul fsync | Configurable: batch_size + batch_timeout 50ms par defaut | Benchmark: throughput writes avec batching vs sans | Tests: durabilite garantie avec batching - crash test complet | Group commit: +300% throughput writes, durabilite intacte |
| 23 | Performance Extreme | 02/11->06/11 | Runtime stats: mesurer rows_actual vs rows_estimated post-exec | Feedback loop: corriger stats si erreur estimation > 2x | Adaptive join: switcher NestedLoop -> HashJoin si sous-optimal | Cardinality learning: histogramme online mis a jour background | Tests: optimizer converge vers plan optimal apres 3-5 executions | Adaptive optimizer: plans s'ameliorent automatiquement a l'usage |
| 24 | Performance Extreme | 09/11->13/11 | YCSB workload A: 50% read / 50% update - implementer | Workloads B (95/5 read), C (100% read), F (read-modify-write) | Comparer NoeDB vs SQLite sur YCSB A, B, C - meme hardware | Graphes results avec plotters crate, exportes en PNG | Post LinkedIn: YCSB benchmarks NoeDB v2 + tag v1.2.0-perf | YCSB suite complete publiee, resultats comparatifs, tag v1.2.0 |
| Phase 4 -- Distributed Elite ¦ Semaines 25-36 |  |  |  |  |  |  |  |  |
| 25 | Distributed Elite | 16/11->20/11 | Lire section 6 paper Raft: joint consensus algorithm | C_old,new: phase de transition deux configurations simultanees | Implementer AddVoter RPC: proposer nouveau membre | Implementer RemoveVoter: retrait membre du cluster | Tests: cluster 3->5 noeuds sans downtime, coherence maintenue | Joint consensus: membership changes 3->5->3 noeuds valides |
| 26 | Distributed Elite | 23/11->27/11 | Pre-vote phase: Candidate demande si il gagnerait sans perturber | Leader stickiness: follower rejette vote si leader recent (100ms) | Check quorum: leader verifie sa majorite sur les reads | Tests: pre-vote empeche elections parasites en partition reseau | Mesurer: MTTR avant/apres pre-vote - cible < 200ms | MTTR < 200ms, elections perturbantes eliminees |
| 27 | Distributed Elite | 30/11->04/12 | ReadIndex protocol: leader confirme sa legitimite avant read | Lease-based reads: leader utilise clock lease, pas de round-trip | Follower reads: follower attend applied_index >= read_index | Read routing: client peut lire depuis n'importe quel noeud | Tests: linearizability verifiee - Jepsen-style checker | Reads distribuees sur followers: throughput lectures x3 |
| 28 | Distributed Elite | 07/12->11/12 | LeaderTransfer RPC: leader cede volontairement a un noeud cible | Forced election: target recoit TimeoutNow -> elit immediatement | Use case: rolling restart sans downtime cluster entier | Tests: transferer leader 10x -> latence spike < 50ms chaque fois | CLI: noedb-cli raft transfer-leader --to node2 | Leader transfer < 50ms, rolling restart zero-downtime |
| 29 | Distributed Elite | 14/12->18/12 | 2PC: Coordinator envoie PREPARE a tous les shards participants | Participant: voter YES si txn committable, persister vote sur WAL | Coordinator: si tous YES -> COMMIT global, sinon ABORT global | Failure recovery: coordinator crash -> participants timeout -> abort | Tests: bank transfer cross-shard, 0 incoherence sur 10k txns | 2PC distribue: atomicite cross-shard garantie mathematiquement |
| 30 | Distributed Elite | 21/12->25/12 | ShardMap: range-based sharding (cle -> shard_id via consistent hash) | Chaque shard = groupe Raft independant avec son propre storage | Router: client envoie query -> bon shard automatiquement | Shard split: diviser un shard surchargé en 2 avec rebalancing | Tests: 3 shards x 3 noeuds = 9 noeuds, queries routees correctement | Multi-raft sharding: 3 shards operationnels, routing automatique |
| 31 | Distributed Elite | 28/12->01/01 | Distributed SeqScan: paralleliser scan sur tous les shards | Distributed aggregation: COUNT/SUM sur shards -> merge coordinator | Distributed JOIN: broadcast ou hash partition selon taille tables | Query coordinator: plan d'execution distribue multi-shard | Benchmark: query distribuee 3 shards vs 1 shard - overhead mesure | Cross-shard SELECT avec agregats: overhead < 30% |
| 32 | Distributed Elite | 04/01->08/01 | Shard metrics: rows_count, bytes, write_rate par shard | Auto-split: shard > 1GB -> trigger automatique de split | Auto-balance: migrer shard du noeud le plus charge au moins charge | CLI: noedb-cli cluster status -> affichage heatmap par shard | Tests: 10M rows -> auto-split -> balance automatique verifie | Auto-rebalancing: cluster equilibre sans intervention manuelle |
| 33 | Distributed Elite | 11/01->15/01 | Tests partition reseau: bloquer trafic inter-noeuds via namespaces | Verifier: partition 2/3 -> 1 seul leader elu dans majorite | Verifier: partition guerie -> resynchronisation < 2 secondes | Chaos: delais reseau 0-500ms aleatoires -> cluster stable | Chaos: packet loss 5% -> toujours coherent apres 24h | Rapport 48h chaos reseau: 0 split-brain, 0 corruption donnees |
| 34 | Distributed Elite | 18/01->22/01 | Lag metrics: replication_lag_bytes, replication_lag_seconds | Back-pressure: ralentir writes si follower trop en retard (> 100MB) | Configurable max_replication_lag: 100MB ou 5s par defaut | Tests: follower lent -> back-pressure -> leader ne sature pas RAM | Alertes Prometheus: lag > seuil -> warning log + metric | Back-pressure actif: OOM leader impossible, lag controle |
| 35 | Distributed Elite | 25/01->29/01 | Snapshot complet: serialiser LSM + Raft state -> archive | opendal crate: upload snapshot vers S3 / MinIO / Cloudflare R2 | Restore: telecharger snapshot + replay WAL depuis object store | Incremental backup: WAL segments uploades contiguement | Tests: backup complet -> drop toutes donnees -> restore -> data identique | Backup/restore S3 fonctionnel, disaster recovery teste OK |
| 36 | Distributed Elite | 01/02->05/02 | Benchmark: throughput cluster 3 noeuds writes/s en release mode | Benchmark: throughput reads distribuees (tous followers) | Latence P99 end-to-end: client -> shard -> storage -> response | Comparer: NoeDB cluster vs standalone Postgres sur meme hardware | Post LinkedIn: phase distributed complete + tag v1.3.0-distributed | Benchmarks distribues publies, tag v1.3.0-distributed |
| Phase 5 -- Query Engine v2 ¦ Semaines 37-44 |  |  |  |  |  |  |  |  |
| 37 | Query Engine v2 | 08/02->12/02 | Parser: OVER (PARTITION BY ... ORDER BY ...) syntax complete | WindowSpec struct: partition_cols, order_cols, frame_spec | ROW_NUMBER(), RANK(), DENSE_RANK() executors implementes | SUM() OVER, AVG() OVER, LAG(), LEAD() avec offset | Tests: 20 queries window functions -> resultats identiques Postgres | Window functions: ROW_NUMBER, RANK, LAG, LEAD, SUM OVER |
| 38 | Query Engine v2 | 15/02->19/02 | Parser: JSON literals, -> et ->> et #>> operators | Type JsonValue: CBOR binaire stocke dans SSTable | json_extract(), json_object(), json_array() builtins | JSONB indexing: index B-Tree sur champ JSON data->>'user_id' | Tests: INSERT JSON -> SELECT ->> -> filter sur champ JSON | JSON/JSONB first-class: read/write/index sur sous-champs |
| 39 | Query Engine v2 | 22/02->26/02 | Inverted index struct: token -> list of (doc_id, positions) | Tokenizer: split, lowercase, stemming (Porter Stemmer en Rust) | CREATE INDEX fts ON articles USING FULLTEXT (body) | MATCH(col) AGAINST('rust database') - query planning + execution | Tests: 100k articles indexes -> search latence < 5ms | Full-text search: index inverse, requetes MATCH AGAINST < 5ms |
| 40 | Query Engine v2 | 01/03->05/03 | Parser: WITH name AS (SELECT ...) - CTE syntax | CTE executor: materialiser CTE en table temporaire en RAM | Recursive CTE: WITH RECURSIVE - graphes et arbres hierarchiques | Optimisation: CTE inlining quand referencee une seule fois | Tests: hierarchie employes via recursive CTE -> resultats corrects | CTE + RECURSIVE operationnels, requetes hierarchiques |
| 41 | Query Engine v2 | 08/03->12/03 | Parser: COPY table FROM STDIN - CSV format | Batch insert: parser CSV -> inserer 10k rows par batch Raft | Binary COPY: format binaire plus rapide que CSV | Parallele: diviser gros fichier en chunks -> insert concurrent | Benchmark: COPY 10M rows -> throughput cible 500k rows/s | COPY bulk: 500k+ rows/s, bulk loading production-grade |
| 42 | Query Engine v2 | 15/03->19/03 | Integrer wasmtime crate: executer WASM modules sandboxes | CREATE FUNCTION my_func LANGUAGE wasm AS binary - SQL DDL | Sandbox: UDF ne peut ni lire storage ni acceder reseau (capabilities) | Type bridge: Rust Row -> WASM linear memory -> resultat type | Tests: UDF compilee en WASM appelee depuis SQL - resultats corrects | WASM UDFs sandboxees: extensibilite NoeDB sans recompiler |
| 43 | Query Engine v2 | 22/03->26/03 | Uncorrelated subquery: SELECT (SELECT COUNT(*) FROM orders) | Correlated subquery: WHERE (SELECT SUM FROM orders WHERE uid=u.id) | Subquery decorrelation: transformer en JOIN quand possible (anti N+1) | EXISTS / NOT EXISTS operators - pushdown vers storage | Tests: 10 correlated subqueries -> corrects + 0 N+1 query | Subqueries correlees/decorrelees, EXISTS/NOT EXISTS optimises |
| 44 | Query Engine v2 | 29/03->02/04 | TPC-H inspired: 8 queries analytiques complexes avec JOINs | Mesurer chaque query: P50/P95, memoire, plan choisi | Comparer vs DuckDB sur meme hardware - OLAP benchmark | Profiling final phase 5: flamegraph -> dernieres optimisations | Tag v1.4.0-query-v2, changelog, post LinkedIn query engine | TPC-H benchmark publie, tag v1.4.0-query-v2 |
| Phase 6 -- Observabilite & Fiabilite ¦ Semaines 45-48 |  |  |  |  |  |  |  |  |
| 45 | Observabilite & Fiabilite | 05/04->09/04 | metrics crate: counters, histogrammes, gauges - tous modules | /metrics endpoint HTTP pour scraping Prometheus | Traces OpenTelemetry: span par query SQL + Jaeger exporter | Grafana dashboard: latence, throughput, Raft lag, cache hits | Alertes: P99 > 100ms -> alert, leader absent > 2s -> alert PagerDuty | Observabilite complete: Prometheus + OTEL + Grafana dashboard |
| 46 | Observabilite & Fiabilite | 12/04->16/04 | Integrer madsim crate: simuler reseau + temps deterministiquement | Reecrire tests Raft avec madsim: inject network failures | proptest: generer sequences aleatoires d'ops sur storage + Raft | 1000 seeds x cluster 5 noeuds -> verifier 0 violation securite | Rapport: madsim coverage, bugs trouves, invariants prouves | madsim 1000 seeds: 0 violation invariant Raft, bugs crush |
| 47 | Observabilite & Fiabilite | 19/04->23/04 | cargo-fuzz sur parser SQL: 48h fuzzing continu LibFuzzer | cargo-fuzz sur protocol wire: frames malformees / tronquees | cargo-fuzz sur LSM storage: entrees corrompues / taille 0 | AddressSanitizer + MemorySanitizer: 0 UB ni memory error | ThreadSanitizer: 0 data race sur 10k thread interleavings | 48h fuzz sans crash, 0 memory error, 0 data race - certifie |
| 48 | Observabilite & Fiabilite | 26/04->30/04 | Chaos monkey: tuer noeuds aleatoirement toutes les 10s pendant 1h | Mesurer: availability % sur 1h de chaos continu | RTO: mesurer temps recovery exact apres crash leader | RPO: mesurer donnees perdues maximales apres crash en ecriture | SLA document: NoeDB garantit RTO < 500ms, RPO = 0 avec 3 noeuds | SLA documente et prouve par tests: RTO<500ms, RPO=0 |
| Phase 7 -- Ecosystem & Launch v2.0 ¦ Semaines 49-52 |  |  |  |  |  |  |  |  |
| 49 | Ecosystem & Launch v2.0 | 03/05->07/05 | Python driver: noedb-py sur PyPI (asyncio + sync via grpcio) | Go driver: noedb-go sur pkg.go.dev (gRPC + connection pool) | Node.js driver: @noe/noedb-client sur npm | Tests cross-driver: memes queries Python/Go/Node -> resultats identiques | Docs API pour chaque driver + exemples quickstart | 3 drivers publies: PyPI, pkg.go.dev, npm - cross-language teste |
| 50 | Ecosystem & Launch v2.0 | 10/05->14/05 | PgBouncer-like pool en Rust: min/max connections configurables | Health check periodique des connexions dans le pool | Transaction-level pooling: connexion rendue apres COMMIT | Load balancer: router reads -> followers, writes -> leader | Tests: 1000 connexions simultanees -> pool gere sans OOM ni panic | Connection pool: 1000 connexions gerees, load balancing actif |
| 51 | Ecosystem & Launch v2.0 | 17/05->21/05 | mdBook setup: structure Architecture + Storage + Raft + Query | Storage internals: LSM, MVCC, compaction, XOR filter expliques | Distributed guide: Raft, joint consensus, 2PC, sharding expliques | Query engine guide: planner, SIMD, adaptive optimizer expliques | Tutorial: 'Build a banking app on NoeDB in 10 minutes' - complet | mdBook deploye GitHub Pages, docs completes, tutorial fonctionnel |
| 52 | Ecosystem & Launch v2.0 | 24/05->28/05 | GitHub release v2.0.0: changelog complet depuis v1.0.0 | Twitter/X thread: 'I shipped NoeDB v2.0 from Cameroon' | Hacker News Show HN: NoeDB v2.0 - distributed SQL engine built in Africa | Dev.to + Medium: '12 months building NoeDB v2 - MVCC, SIMD, Raft' | Repondre commentaires, merger PRs, celebrer - Noe Engineering est reelle | LAUNCH v2.0 - target 1000+ stars, recruits inbound |